Advanced           Instructor Guide

Introduction         Training Manual

Project 2007

Best Training www.microsofttraining.net

Microsoft Office Project 2007 Introduction Courseware

Best Training 2007

Table of Contents

Section 1: Getting Started	1

Lesson 1.1: Starting Out	2

What is Microsoft Office Project 2007?	2

What is a Project?	2

Why Use Project 2007?	3

What’s New in Project 2007?	3

Lesson 1.2: Meeting Project	6

Opening Project 2007	7

Interface Overview	9

Menus and Toolbars	10

Shortcut Keys	14

Dialogue Boxes	15

Using the Project Guide Task Panes	17

Closing Project 2007	19

Lesson 1.3: Using Project	20

Menu Overview	20

Using the Standard Toolbar	21

Using the Formatting Toolbar	23

Using the Project Guide	24

Lesson 1.4: Managing Project Files	27

Opening Project Files	27

Saving Project Files for the First Time	30

Re-Saving a Project File	31

Switching Between Open Projects	32

Closing Project Files	33

Lesson 1.5: Getting Help in Project	34

Using the Help Menu	34

Using the Help Window	35

Using the Type a Question Box	40

Getting Help in a Dialogue Box	42

Section 1: Review Questions	44

Section 2: Starting a Project	46

Lesson 2.1: Creating a Project	47

Planning your Project	47

Creating a Project	48

Entering Project Information	49

Setting Working Time	50

Using the Project Guide	57

Lesson 2.2: Creating Tasks	64

Entering New Tasks	64

Changing a Task’s Duration	65

Moving a Task	66

Inserting a Task	66

Deleting a Task	67

Lesson 2.3: Editing Tasks	68

The Task Information Dialogue	68

Task Types	69

Setting Milestones	72

Creating Recurring Tasks	73

Creating Sub Tasks	75

Creating Summary Tasks	76

Lesson 2.4: Setting Constraints	79

Types of Constraints	79

Creating a Constraint	80

Setting Task Deadlines	82

Constraints versus Deadlines	83

Section 2: Review Questions	85

Section 3: Scheduling a Project	87

Lesson 3.1: Creating the Project Calendar	88

Calendar Types	88

Setting up the Calendar	89

Creating a New Calendar	91

Using Calendar View	93

Adjusting the Timescale	95

Lesson 3.2: Setting a Project Baseline	98

Baseline Basics	98

Saving a Baseline	99

Viewing a Baseline	102

Clearing a Baseline	106

Lesson 3.3: Setting an Interim Plan	107

Setting an Interim Plan	107

Viewing an Interim Plan	108

Clearing an Interim Plan	109

Lesson 3.4: Setting the Critical Path	111

What is the Critical Path?	111

How Does Project Determine a Critical Path?	111

Viewing the Critical Path	112

Shortening the Critical Path	116

Section 3: Review Questions	118

Section 4: Printing and Viewing a Project	120

Lesson 4.1: Basic Editing Tasks	121

Checking Spelling	121

Selecting Text	122

Cutting, Copying, and Pasting	123

Using Undo and Redo	124

Inserting Page Breaks	125

Lesson 4.2: Changing Your View	127

Using Zoom	127

Using the View Bar	130

Using Basic Views	132

Using Advanced Views	132

Using the Find Dialogue	134

Lesson 4.3: Using Page Setup	137

Setting Page Options	137

Setting Margins	138

Setting Headers	139

Setting Footers	141

Modifying the Legend	142

View Settings	143

Lesson 4.4: Printing a Project	145

Opening Print Preview	145

Using Print Preview	146

Using Print Commands	147

Using the Print Dialogue	148

Using the Project Guide to Print your Project	149

Section 4: Review Questions	153

Index	155

Section 1: Getting Started

In this section you will learn:

- What Project 2007 is

- What is new in Project 2007

- How to open Project 2007

- How to use the Project Guide panes

- About the Project 2007 interface

- How to use menus and toolbars

- How to open Project files

- Haw to save Project files

- How to switch between open projects

- How to close Project files

- How to use the Help menu

- How to use the Help window

- How to get help in a dialogue box

Lesson 1.1: Starting Out

Welcome to Microsoft Project 2007! In this lesson, we’re going to focus on the basics: what Project 2007 is, what a project is, and how Project 2007 can help you.

### What is Microsoft Office Project 2007?

As you might guess, Project 2007 is aimed towards project management, which is the art of aligning resources and schedules to accomplish all of the various tasks that comprise a project.

Other Microsoft applications, like Excel or Word, can be used in a very general way. That is to say, you can use a program like Word to compose and format practically anything that you need to present as written work. In Excel, you can build a worksheet to analyze just about any type of information that is suited to a tabular format.

Project, on the other hand, has a more specific focus. This program is designed as a tracking and planning tool for large (or small) endeavors that involve sub tasks, multiple resources, and various scheduling goals and priorities. This does not mean that Project lacks versatility. You can use Project to help plan and organize anything from a software development process, to a major construction job, to the expansion of a company.

Let’s say you’re the head writer for the Acme Widget Company. You have to prepare the company’s annual report, which has a big budget, requires co-operation from many departments, and is going to take about six months to plan. You can use Project to manage all the tasks that must be performed to make sure they are assigned, completed, and stay on budget. You can also use Project to generate reports and calendars for others, to demonstrate the current level of progress, and to provide informative projections as to the completion of the project’s stages.

### What is a Project?

The Oxford English Dictionary defines a project as “an enterprise carefully planned to achieve a particular aim.” So, for an elementary school student, a project might be a report with statistics, pictures, and facts about a country, with the aim of learning about that country.

In a business sense, a project is an undertaking that will accomplish a specific task, such as the launch of a new product, an office party, or writing a report. These projects are unique; once the project is complete, you will have a tangible result.

Projects can come in all shapes and sizes. A project to plan an office party, for example, may only consist of a dozen tasks and only need a few resources. It may only take a week or so to complete. On the other hand, a more complex project, such as the launch of a new product, may have thousands of tasks and resources. It may even have sub-projects, such as research, development, production, and marketing. All of these components may take years to complete.

### Why Use Project 2007?

There are a number of good reasons to use Project 2007. For one, you will probably find its interface very familiar. The menus, toolbars, and general interface structure follow the familiar design concepts seen in many other popular Microsoft applications.

Another reason is that it is designed specifically for project management. Whether you’re undertaking a two-week project or a major company reorganization that will take years, you will find all the resources that you need within Project 2007.

Having all these resources in one place will also help you stay organized. This is especially important in a long-term project; if someone else has to take over project management, they will appreciate being handed a single file with all the information, rather than multiple file folders full of disorganized paper. Managing the project digitally also makes it easy to back the project up, assign tasks to other people, and print reports.

Finally, very few major projects come to completion without a hitch. The larger your project is, the more variables you will have to account for. A dynamic management tool like Project makes it easier to readjust if problems arise, like the unforeseen loss of a resource, or a scheduling delay due to factors beyond your control.

### What’s New in Project 2007?

While Project 2007 maintains a familiar interface layout that is quite similar to earlier versions, it does contain some significant functional improvements over its predecessors.

Some of the new features in Project 2007 are:

Visual Reports

The new visual reports features allow you to use Microsoft Excel and Visio to create slick PivotTables, charts, and Pivot Diagrams based on your Project data.

(Note: To use the visual reports feature, you may have to install the .NET framework, available from Microsoft.)

Multi Level Undo

In Project 2007, you can make, reverse, and redo changes by using the new multi-level undo feature. With this feature, you can undo changes that you made to views or data, as well as actions or groups of actions performed by macros. You can use this feature to correct typos that were performed several steps back, or even to backtrack and test different What If scenarios.

Change Highlighting

This new feature allows you to automatically highlight all items in your project that are readjusted in response to some change that you make.

Task Drivers

If your project contains hundreds or even thousands of tasks, it can be hard to determine exactly which items are dependent on which. In Project 2007, you can display information about what is driving a particular task (what it is dependent on) by selecting it, and then choosing the Task Drivers option from the Project menu.

The Task Driver pane will provide information on the predecessors of the selected task, as well as a link to the calendar of a resource or resources assigned to the task.

Costs and Budget Features

In Project 2007, a cost can be implemented as a resource, like materials or work. Now, you can assign multiple non work-related costs to a given task as you see fit. Also, in previous versions of Project, budget costs were calculated as work was accomplished, in a bottom up fashion. In Project 2007, you can assign a budget to an entire project, allowing you to take a top down approach.

Calendar Exceptions and Effective Dates

In Project 2007, you can choose to use to use effective dates and calendar exceptions. If you use Project’s traditional calendar model, it can be difficult to model a resource that has different work periods comprised of varying days or weeks. If your project involves this type of scheduling, Calendar Exceptions and Effective Dates can make your job easier.

Revised Custom Field Structure

Project 2007 has a revised custom field structure that can improve how information is utilized and communicated in conjunction with Project Server. (Note: Project 2007 Standard cannot be fully used with Project Server as it is intended for stand alone use. To work with Project server, you must use the Professional version of Project.)

Lesson 1.2: Meeting Project

Now that you know what Microsoft Project 2007 is, and why you might want to use it, it is time to go over the most basic concepts required to use it.

In this lesson, you will learn how to open Project 2007. You will also learn about the key interface components, how to use task panes, and how to close Project 2007.

### Opening Project 2007

There are two ways to open Microsoft Project 2007. The first is with the icon on your desktop. To open Project 2007, move your mouse pointer over the Microsoft Project 2007 icon, and double click, like this:

Once you perform this action, the Project 2007 screen will open.

You can also find Microsoft Project 2007 in your Start menu. Follow the steps listed below to find Project in your Start menu. (Note that some steps have two methods as they apply to both users of Windows 2000 and Windows XP.)

- Click the Start button in the bottom left hand corner of your screen.

- Choose Programs or All Programs.

- Click the Microsoft Office option.

- Click the Microsoft Office Project 2007 option.

### Interface Overview

When you open Project 2007, you should see a screen that looks like the following.

Don’t get overwhelmed by all these parts; we’re going to explain what each of them is, and we’ll get into each part in depth later on. For now, don’t worry if a certain part’s purpose isn’t clear.

| Title Bar (1) | This tells you what program you’re working in (Microsoft Project) and what project (Project1). By default, Microsoft Project 2007 names unsaved projects Project1, Project2, and so on. |
| --- | --- |
| Menu Bar (2) | Click any of these commands to see a list of possible options, then, click any of the options to perform that action. |
| Type a Question (3) | If you have a question, type it here! |
| Document Controls (4) | These buttons let you minimize (), maximize/restore (), or close () a certain project or the Project application. |
| Toolbars (5, 6) | Toolbars have icons, which are small buttons with pictures that represent actions. When you click the button, that action will happen. For example, you could click the icon on the standard toolbar and your project would save. |
| Task Panes (7) | Task panes can display lots of different information, functional options, wizards, or links to other task panes or resources. You can navigate through task panes almost like pages in a browser. |
| Project Window (8) | This is where you will enter your project’s task information. In this image, you can see the task entry panel on the right and the Gantt chart (with dates listed at the top like a timeline) on the left. |
| Status Bar (9) | This bar can provide information on the current status of your application. |
| Scroll Bars (10, 11, 12) | Use these bars to view different parts of your window. You can use the arrows to move the view to the left or right, or drag the scroll bar to where you want it. |

### Menus and Toolbars

Two other important components of the Project 2007 interface are menus and toolbars. Along the menu bar near the top of the project screen you will see a series of menu options. If you are familiar with other Microsoft programs, you are probably already somewhat comfortable using menus.

Toolbars are bars containing a series of clickable button (icon) controls. Often the controls available in toolbars are also available from the menus. The buttons on the toolbars normally are the most frequently used menu options.

| Buttons/Icons | Just like icons on your desktop, toolbar icons are small buttons with pictures that represent actions. When you click the button, that action will be performed. Icons are mostly seen grouped on the toolbars. For example, you could click the icon on the standard toolbar and your project data would be sent to the printer. If you let your mouse pointer hover over an icon, a small box describing the icon’s function will appear as shown: If you are unsure about what a particular button does, look for the description that appears. |
| --- | --- |
| Drop-down menus | You can use these menus to pick from a number of choices. With some menus, you can type in your choice. A good example is the Group menu on the toolbar, which looks like this: . You can click where it says No Group and type an option directly, or you can click the small arrow at the right of the field and choose an item from a list of options. |
| Menu items | If you click on a menu heading in the menu bar at the top of your Project screen (like, File, Edit, Window, or Help), the menu will expand to show a list of commands. You can then click on any item to perform that action. In the sample to the left, we’ve clicked on the Project menu. Now, we can click any of the items below it to perform that action. |
| Expanding menu items | Some menu items have a right-facing arrow () beside them. This means that once you click on (or put your mouse over) that item, an additional menu will show up (called a sub-menu). In the image on the left, you can see that we chose Outline, revealing a sub menu of options that we can choose from. |
| Checked items | Some items in a menu may have a check next to them or a box around them. This means that the item is turned on or enabled. If it has a check, you can normally turn the command off by clicking it, which will uncheck it. Other items can’t be unchecked; you must choose another item to switch. |
| Chevrons | In the sample on the right, do you see the two stacked arrows at the bottom of the menu? Those are called chevrons. Microsoft Project only shows you the items you have (or the items it thinks you will) use most by default. To see the rest of this menu, click the chevrons. (The menu may also automatically expand after it’s been open for a few seconds.)Then you’ll see the entire menu. You may notice that items that were in the shortened menu have a lighter color next to them. You may also notice that certain menu items have a series of ellipses (dots) following them. Three dots following a menu item indicate that there is a dialogue box associated with that menu item. |

Another way to open menus is by right-clicking. Right-click menus aren’t like the main menu bar, which stays the same. When you right-click, menus are contextual, which means they change depending on what you’ve right-clicked on.

For example, if we right-click on a toolbar, here’s the menu we see:

This menu lists all of the toolbars that can be found in Project. This menu also allows you to choose which toolbars will be displayed. (The ones with check marks will be available on the Project screen). To remove a toolbar from view, clear the corresponding checkmark in the menu that appears when you right click on any toolbar.

If you right-click on the task area of the Project screen, you will see a very different menu:

Right-click menus can contain any of the types of menu items that we talked about before (menu items, expanding menu items, or icons with menu items). These right click menus are never shortened with chevrons, and they provide a quick and convenient way to perform context related tasks.

### Shortcut Keys

Another way to implement commands in Project is by using shortcut keys. Shortcut keys are key board combinations that, when pressed, perform an action just like clicking a button or a menu item. Sometimes you can see the shortcut keys for a particular Project action in an icon’s ScreenTip or listed next to a menu option. What follows is a list of some of the most commonly used shortcuts in Project.

| Open a new project | Ctrl + N |
| --- | --- |
| Save a file | Ctrl + S |
| Open a file | Ctrl + O |
| Print a project | Ctrl + P |
| Close Project | Alt + F4 |
| Select All | Ctrl + A |
| Copy text | Ctrl + C |
| Cut text | Ctrl + X |
| Paste text | Ctrl + V |
| Find text | Ctrl + F |
| Undo last action | Ctrl + Z |
| Redo last action | Ctrl + Y |
| Check spelling or grammar | F7 |
| Get Help | F1 |

### Dialogue Boxes

Some menu items or shortcut keys will open dialogue boxes. A dialogue box is an extra window that opens up with options. One of the most common dialogue boxes is the one found when you click on the Tools menu and click Options.

Let’s look at the different elements in a dialogue box.

| Tabs | Dialogue boxes can contain options for different items. Click the tabs (usually at the top of the screen) to change dialogue boxes. In the example above, there are 11 different tabs ranging from Interface options to Security settings. |
| --- | --- |
| Drop-down menus | Just like toolbar drop-down menus, you can type in the box or click the down arrow to choose from a list of values. |
| Check boxes | If an item is checked, it means it’s on. If the item is unchecked, it’s off. Click the check box to change this status. |
| Radio buttons | Use these buttons to choose from a list. Like check boxes, click to change the item that is in use. Normally, only one item from the list can be selected. |
| Text boxes | These boxes must be filled out by typing in them. |
| Buttons | Some buttons open more dialogue boxes and allow you to specify advanced settings. |
| OK and Cancel | In any dialogue box, you can click OK to save your changes. You can also click Cancel to discard your changes. (Some dialogue boxes have an Apply button so you can apply your changes right away, before making more changes.) |

### Using the Project Guide Task Panes

In Project 2007, there is a series of task panes known as the Project Guide that are normally found on the left side of the screen. The Project 2007 Project Guide panes provide controls and wizards that will allow you to perform a number of tasks, including defining a project, defining working times, organizing tasks into phases, scheduling tasks, adding custom information, and setting deadlines and task constraints.

These options can be seen in the form of blue hyperlinks on the primary Tasks pane. If you click one of these hyperlinks, the task pane corresponding to the link you click will be displayed.

| Task Pane Title (1) | This title tells you what pane you are currently using. The X at the right of this title bar will close the task pane. |
| --- | --- |
| Task Pane Navigation (2) | Use the arrows to move forward or back through previously viewed panes. |
| Task pane links (3) | These hyperlinks will display the other Project Guide panes. Each link corresponds to a pane containing options that will help you perform the task that the link describes. |

On the toolbar directly above the Project Guide panes, you will see two button controls. The button labeled Tasks will display the default Tasks pane shown above. If you click the small down pointing arrow next to this button, you will display a menu of options for invoking the other panes.

To the left of this Tasks button, you will see a Show/Hide Project Guide button. This button will toggle the Project Guide panes on or off. If a given pane is visible, clicking the button will make it disappear. If no panes are visible, clicking the button will display a pane on screen.

Just as with other Microsoft programs, you will find that there is often more than one way to perform a particular action in Project 2007. As shown above, you can access different Project Guide panes through hyperlinks, forward or back buttons, or by using the Tasks menu.

### Closing Project 2007

To close Project 2007, click the File menu and click Exit.

You can also click the X in the top right hand corner of the window or use the Alt + F4 shortcut.

If you have made any changes to the open project, you will be prompted to save it; we’ll get to that in the next lesson.

Lesson 1.3: Using Project

In this lesson, we’re going to delve deeper into interacting with Microsoft Project 2007. We’ll talk about using the menus, toolbars, and the Project Guide.

### Menu Overview

In our last lesson, we learned how to use the various components of menus. Now, we’ll learn what each menu in Project does.

|  | Restore, move, minimize, maximize, or close the window. |
| --- | --- |
| File | Here, you will find commands to open, save, close, and print your projects. You’ll also find the command to close the project or exit Project 2007 here. |
| Edit | This menu has commands for cutting, copying, pasting, and selecting. Navigation tools such as Find, Replace, and Go To are also located here. You’ll also find commands for working with specific items, such as the Link Task command. |
| View | Change what components are displayed on the Project screen, and change how your data will be displayed. |
| Insert | Add elements such as drawings, tasks, resources, and objects. |
| Format | Change the font, layout, and appearance of your project. |
| Tools | Check your spelling, change the working time, add and manage resources, use macros, and set Project options. |
| Project | Organize your project and enter project information. |
| Report | This menu contains options for producing reports based on Project 2007 presets or by using the new Visual Reports feature. |
| Collaborate | This menu has options that can be helpful for collaborating on a project with the use of Project Server. |
| Window | Split and re-arrange windows, or switch projects. |
| Help | If you have a question, this is the place to look! |

### Using the Standard Toolbar

In our last lesson, we learned how to use toolbars. The toolbar you will use most often will probably be the standard toolbar; this contains many basic commands, such as cutting, copying, pasting, and working with Project elements. Once again, we’ll refer to concepts that you haven’t learned yet. This is just an overview of those elements so that you know where to find them when we do learn about them.

|  | Creates a new project in a new window. |
| --- | --- |
|  | Opens a dialogue to choose a project to open. |
|  | Saves your project. (If you haven’t already specified a name and location for your project, you will be prompted for this information.) |
|  | Prints your document. |
|  | Opens print preview. |
|  | Checks for spelling and grammar errors in your document. |
|  | Cuts the selected text. |
|  | Copies the selected text. |
|  | Pastes text from the clipboard. |
|  | Opens the Format Painter. |
|  | Undoes your last action. |
|  | Redo an action. |
|  | Shows the change highlights. |
|  | Insert a hyperlink. |
|  | Link selected tasks. |
|  | Unlink selected tasks. |
|  | Split a task. |
|  | Open task or resource information. |
|  | Create a task or resource note. |
|  | Find Task Drivers. |
|  | Assign a resource to a task. |
|  | Change how information is grouped. |
|  | Zoom into the project. |
|  | Zoom out of the project. |
|  | Goes to the selected task. |
|  | Copies the selected picture. |
|  | Opens the Project 2007 help window. |

All of these commands are basic buttons: just click the button for the action to happen!

### Using the Formatting Toolbar

The second toolbar that will be open when you open Project 2007 is the formatting toolbar. You can use this toolbar to change the look and display of various project elements. We haven’t learned about any of these concepts yet; this is just an overview so you know where to find the commands when you need them.

|  | Out-dent task. |
| --- | --- |
|  | Indent task. |
|  | Show subtasks. |
|  | Hide subtasks. |
|  | Show or hide task assignments. |
|  | Choose which task levels to show. |
|  | Choose which font to use. |
|  | Choose the font size. |
|  | Bolds the selected text, or turns bold on. |
|  | Italicizes the selected text, or turns italics on. |
|  | Underlines the selected text, or turns underlining on. |
|  | Aligns the text to the left. |
|  | Aligns the text to the centre. |
|  | Aligns the text to the right. |
|  | Change how tasks are filtered. |
|  | Turns AutoFilter on. |
|  | Starts the Gantt Chart Wizard. |

There are several different types of buttons on this toolbar. Most are basic buttons that you can click to make an action happen. Some others have drop-down menus which require you to pick from a list of choices. The Task Filter and Fonts buttons are examples of this type.

If you find that you are missing buttons on a toolbar, click the arrows at the end of the toolbar in question to see a menu of the extra controls that are available.

If you choose Show Buttons on Two Rows from the menu, the toolbars will be displayed on separate rows.

In this image, each task bar is on its own row.

In this image, the toolbars are on the same row.

### Using the Project Guide

The last toolbar that will open by default is the Project Guide. The Project Guide task panes where discussed briefly in the previous lesson. This is what the Project Guide toolbar looks like.

If you click one of these buttons, the guide pane that corresponds to the button will appear on the left of the project screen.

In the image above, you can see that the Track button has been selected, and the Track Project Guide pane is displayed.

These guides will walk you through the process of setting up the corresponding phase or component of your project. You can click on any of the blue links items in the guide to perform that task. As you select different elements, the Project Guide will display the appropriate working area on the right, and change the information and controls displayed in the guide pane as appropriate. You may even see help topic links appear.

Here is the Resource Booking Types Project Guide pane and the associated working area.

To close the Project Guide, click the X in the top right hand corner of the pane (like a standard task pane), or click the Show/Hide Project Guide button () on the Project Guide toolbar.

Lesson 1.4: Managing Project Files

Now that we’re a bit more familiar with how to use Project, we’re going to learn how to work with its files. As you might expect, in Microsoft Project 2007 you create files called projects. These files contain all the elements for your project. In this lesson, we’ll learn how to open, save, close, and switch between Project files.

### Opening Project Files

Opening a file in Microsoft Project 2007 is easy! First, pick one of these commands:

Click the Open button () on the standard toolbar.

Use the Ctrl and O shortcut keys

Click the File menu and click Open.

Any of the actions listed above will display an Open dialogue box like the following.

At the top of the screen, choose where your project is stored.

You can also click one of the icons on the left to go to the corresponding location.

Once you have found your file, click it to select it and click the Open button in the lower right. You can also double click directly on the file to open it.

Then, the file will appear in Project!

### Saving Project Files for the First Time

As we’ve already discussed, a lot of information can go into a project, and it may take considerable time for your project to be completed. For these reasons, it only makes sense that you would want to save your project files throughout the course of the project life cycle.

To save your Project file, pick one of these commands:

Click the Save button () on the standard toolbar.

Use the Ctrl and S keyboard shortcut

Click the File menu and click Save or Save As.

Now, Project will ask you where you want to save the file. First, pick the location for your file from the Save In menu at the top.

Then, type the file name in the File Name field at the bottom of the dialogue.

When you are ready, click the Save button in the lower right to save your file in the specified location.

### Re-Saving a Project File

Once you’ve saved your project to a specific location, you don’t have to re-enter the information to resave your project. Just use one of the Save commands that were mentioned above (Ctrl + S, File menu - Save, or the Save button on the standard toolbar) and Project will update your file.

If you have not previously saved your file, using these commands will invoke the Save As dialogue. If you have previously saved your file, using these commands will resave it to the same location automatically.

If you do wish to save your file with a different name or in a different location, click the File menu and click Save As. That will re-open the Save dialogue that we saw earlier.

### Switching Between Open Projects

Once you become comfortable with Microsoft Project 2007, you may have a number of projects on the go simultaneously. In these situations, Project 2007 will let you have several projects open at the same time.

To open multiple projects, repeatedly use the Open commands that we talked about earlier. When multiple projects are open, click the Window menu to display a list of the open projects:

The project that is currently active will have a check mark next to it. To switch to another project, just click the option for that project.

You will notice some additional tools in the Window menu, but we’ll save those for later.

### Closing Project Files

If you want to close a project, just click the File menu and click Close, or click the small X in the top right-hand corner of the Project window.

If you haven’t already saved your file when you close it, Project will ask you if you want to do so.

Clicking the Yes button will open the Save As dialogue (or update a saved file). Clicking No will close the file and discard all the changes that you made since you last saved it. Clicking Cancel will return you to the project without saving.

Lesson 1.5: Getting Help in Project

Microsoft Project 2007 has hundreds of commands. No matter how many books you read, how much you practice, or how much you use Project, it’s virtually impossible to memorize every command and every tool. Right now, you have this book and maybe even an instructor and classmates to help you out. But what happens after you’re done?

Luckily Microsoft Project 2007 comes with its own help files. Let’s take a look at how to use those files so you’ll be prepared to get help later on.

### Using the Help Menu

As you might have guessed, the Help menu is one of the best ways to get help. For now, we’re just going to get an overview of each option in the menu. We’ll talk about the most important components in a moment.

The first item, Microsoft Office Project Help, will open a Help window on your Project screen that provides several help options. The second option, Microsoft Office Online, opens http://office.microsoft.com (the Office Web site) where you will find links to downloads, help topics, and other resources.

The Microsoft Office Diagnostics option will open the Office Diagnostics dialogue. This can be used if you have performance issues with Project or other Microsoft Office software.

You can set up customer feedback options, document management (Share Point and shared workspaces), and offline editing options using the Customer Feedback Options command.

The About Microsoft Office Project option will provide technical information about the Project program.

### Using the Help Window

If you click the Help menu followed by the Microsoft Project Help option, you’ll see a help window appear on your project screen. (You can also open this window by pressing the F1 key on your keyboard or clicking the help icon  on the standard toolbar.)

Remember, you can use the scroll bar on the left of the help window to see any information that is out of view.

If you are not connected to the Internet, your help window may look like this.

If you click the small “Show me offline help from my computer” link, help options stored on your local system will be displayed in the window.

Online Help

When you display the help window, you will see a screen displaying a number of hyperlinks. If you click on any of these hyperlinks, you will be presented with additional hyperlinks that are more specific to the subject you are finding help on.

As an example, if you click on the File management hyperlink in the help window…

… Another selection of hyperlinks more specific to the subject of file management will be displayed in the window.

If you continue to follow the links, you will get even more specific subject headings until you reach the information and instructions that are closest to what you are looking for.

Near the top of the help window, you will see a toolbar.

You can click the back and forward buttons () to move between pages that you have visited in the help screen. (These buttons behave very much like the back and forward buttons in a web browser.)  You will also notice a Refresh button and a Home button (house icon). Clicking on the Home button will take you to the original online help screen that you started with. There is also a table of contents button () if you prefer to work through a table of contents like the one shown below.

You can print the information in the help window by clicking the printer icon in the help window toolbar, and you can make sure the Help screen stays visible while you are working with Project by clicking the keep on top button().

You can refine your search for help topics by specifying a particular section of help topics to be searched, using the search tools near the top of the window.

In this example, macro is the search topic and Developer Reference is the category of help resources that will be focused on. When you are ready, just click the word Search to find the results. If you want to close the help window, simply click the close button (X) in the upper right corner of the help window.

Offline Help

It may sometimes be the case that you need help with Project, but an Internet connection is not available. In this instance there is still an offline help option that you can take advantage of.

When you display the help screen without an Internet connection, it may look like the following.

If you click on the “Show me offline help from my computer” link, you will see a window of options like the following.

Each one of the subject links on this page will lead to information that is stored locally on your computer. To follow the links you just have to click on them. Each link will take you to more specific subject links that you can follow until you find the information that is closest to what you are looking for.

The search option and the table of contents are still available to you just as they were in online help, but in offline help there will be significantly less information at your disposal. For this reason, it is a good idea to use online help if you are able to.

### Using the Type a Question Box

In the top right hand corner of your screen, under the close button, you will see this box:

In this box you can type a question, phrase, or word related to the subject you are curious about, and hit the Enter key. A help window will open and your results will be displayed there. You can then proceed to follow the any links that are returned as results in the same way as discussed previously.

### Getting Help in a Dialogue Box

Many dialogue boxes have their own help topics. Just click the Help button at the bottom of the screen (often next to the Close button):

Once you click Help, help results will appear in a help window just as if you’d clicked a help subject link as described previously.

The topics in the help window will be directly related to the dialogue box you’re using. You will notice that the results in the above window deal with assigning resources. All of the toolbar controls and content links in this help window will work in the usual way.

Section 1: Review Questions

- To open Project 2007 you can…

- Use the Windows Start menu

- Use the desktop icon

- Double click on a project 2007 file

- Any of the above

- Which command will open the Open dialogue?

- Ctrl + O

- Ctrl + S

- File - Start

- File - Most Recently Used

- Project 2007 is designed for….

- Project management and scheduling

- Word Processing

- Analysis of financial data

- Creating impressive presentations

- Which of the following is new in Project 2007?

- Gantt Charts

- Multi level undo

- Redo

- Critical Paths

- Thee dots (…) after a menu item indicates what?

- A sub menu

- A keyboard shortcut

- A dialogue box

- That the action cannot be undone

- Which of the following is not on a Project 2007 toolbar?

- The Indent button

- The Save button

- The Copy Project button

- The Undo button

- How do you save a Project 2007 file?

- The Save button

- File - Save

- Ctrl + S

- Any of the above

- Which of the following statements is true?

- There is only one way to use each feature in Project.

- There are usually multiple ways to use a feature in Project.

- All Project features are used in the same way.

- All Project features are accessible through dialogue boxes.

- Online help requires a(n)…

- Help menu

- Mouse

- Help task pane

- Internet connection

- The keyboard shortcut to save a file with the Save As dialogue is…

- F12

- Ctrl + W

- S

- None of the above

Section 2: Starting a Project

In this section you will learn how to:

- Plan a project

- Create a project

- Enter project information

- Set the working time

- Enter tasks

- Change a task’s duration

- Move a task

- Insert a task

- Delete a task

- Open the Task Information dialogue

- Set milestones

- Create recurring tasks

- Create sub tasks

- Create summary tasks

- Set constraints

- Set deadlines

Lesson 2.1: Creating a Project

In the last section you learned the basics of using the Microsoft Project 2007 application. In this section, you will learn how to start our very own project. To start off, we’ll plan and create a new project and enter some basic information for it.

### Planning your Project

Before you even open Microsoft Project 2007, you need to do some thinking about your project. You should always have a plan before you start your project. For a small project, you may be able to map it out in your head. For larger projects (such as the one we’re going to undertake) you’ll probably want to get out a pen and paper (or use a word processor) and make a few lists.

First, create a general outline of the project. You’ll want to think about what the end result of the project will be. You’ll also want to think about the general timeline, budget, and resources that you will have available.

Next, get down to some specific planning. First, create a task list. In this list you may want to specify how long each task is going to take, which tasks are going to be dependent on others, and which ones may need to be broken down into sub-projects.

Once you’ve figured out what your project tasks are going to be, make a list of resources. Estimate what resources will be needed and what resources will be available. If your resources are people, think about the amount of hours they will work on a given task.

Last but not least, think about your costs. You may even want to prepare a formal budget.

For an example project, let’s imagine that you are managing the development of a small software application. (Don’t worry if you don’t know very much about software development. You don’t need any special knowledge about programming or the software development process to follow this example.)

Our project will cover the entire development process, from the initial planning stages to the final delivery of our product to the users. This will serve as a good example project because it contains a number of clearly defined tasks, some of which are sequential (need to be achieved one at a time), while others can be achieved in parallel (more than one task being tackled at the same time). In addition, there will also be tasks that can be broken down into smaller sub tasks.

The following is a tentative list of tasks that we need to perform to develop a basic software product for our client.

Keep in mind that this list is quite tentative, and that tasks may need to be re-arranged or added, but it’s a start!

### Creating a Project

When Microsoft Project 2007 opens, you will see a blank project working area. If you want to open another blank project area, click the New Project icon () on the standard toolbar, or use the Ctrl + N shortcut.

If you click the File menu and click New, you’ll see the New Project task pane on the left of your screen.

To start a new project, you can click the Blank Project link near the top of the New Project task pane. (The other links in this task pane will be addressed in the Intermediate manual.)

### Entering Project Information

The first step in creating your project is to enter your project’s information in the Project Information dialogue box. To open this dialogue, click the Project menu followed by the Project Information option.

When you perform this action, you will see the Project Information dialogue.

On the left hand side of this dialogue, you can enter the project’s start and finish date. You can also choose to schedule from the project start date or the finish date, to start tasks as soon or as late as possible.

On the left hand side of the dialogue, the current date is displayed. You can also set a date to report various statistics about the project. And, you can choose what calendar you want to use and what priority this project will have. (Notice that the default calendar type is Standard.)

Typically, you’ll only want to modify the fields on the left hand side. Note that you can only modify the start or the finish date; Project will calculate the opposite value once you have entered task information. You can choose between modifying the start date, or the finish date, by using the options in the Schedule From drop list.

Once you’ve set your project’s information, click the OK button. You can always come back at any time and modify this information if you wish.

### Setting Working Time

The next thing you’ll need to do is set your working time. This will enable Project 2007 to calculate how long tasks will take to complete. To set up your working time, you can open the Change Working Time dialogue by clicking the Tools menu, followed by the Change Working Time option.

Performing this action will open the Change Working Time dialogue. In this dialogue, you will see a visual representation of a calendar, a legend showing how to interpret the calendar days, a Create New Calendar button, and a grid area with two tabs labeled Exceptions and Work Weeks.

The legend on the left tells you how to interpret the different calendar days (nonworking and exception days are shaded and working days are not shaded). As you can see in the default Standard calendar, Saturdays and Sundays are non working days.

If you click on a given day in the calendar, you will see the working hours for that day just to the right of the calendar. For August 7, the working hours are 8:00 to 12:00 for the morning and 1:00 to 5:00 for the afternoon. (This is based on the default standard calendar.)

Let’s say that you would like to take August 16 and 17 off. To proceed, click August 16 on the calendar to select it, and enter a name (like “Day Off”) in the top Name field under the Exceptions tab. (You can put your cursor in the name field by clicking in it.)

After you enter a name for the exception day, press your Enter key, and then click on August 17. Next, enter a name for the second exception day and press Enter. Now you will have two (shaded) days off specified in your calendar as non working days. You should also notice that the days off are underlined in the calendar.

If you select the name of one of the exception days under Exceptions tab and click the Delete button, it will be removed from the list of exceptions and be listed as a regular working day in the calendar.

Now, let’s suppose that you will only work half a day on Mondays. To accomplish this, click in the calendar on the first Monday that you will work as a half day (August 21 in this example).

The next step is to click in the next available name field under the Exceptions tab to place your cursor there. Type a name (like Half Day) for this calendar exception in the name field. If you press the Enter key to enter the exception, your dialogue should look something like this.

Now, click on the name of your new exception to select its entry under the exceptions tab. When you do this, the Details button on the right will become accessible.

If you click this Details button, you will see the following Details dialogue.

In this dialogue, select the Working Times radio button near the top, and then enter your working hours for your half day as you wish (perhaps 8:00 AM to 12:00 PM) in the From and To fields provided.

When you have entered your hours, you can then select the most appropriate Recurrence pattern for your half days by clicking the Daily, Weekly, Monthly, or Yearly radio button. In this example, every Monday will be a half day, so you should select the Weekly recurrence button.

You can also specify a range of recurrence. You can choose to have the given exception day end after a certain number of the exception days have occurred, or you can choose to end the recurrence by a specified date.

For this example, we will end the half days after 8 occurrences. To see what the dialogue looks like after setting up these options, have a look at the following image.

You will notice that if you select the Weekly radio button for your recurrence pattern, a series of check boxes will be available for choosing the day that your exception will occur on. In this example, of course you should place a check mark by Monday.

When everything is ready, click the OK button to implement the changes you made to the calendar.

As you can see here, the Mondays starting with August 21 are highlighted and underlined.

Monday the 28th is selected, and you can see on the right that the working time for this day is 8:00 to 12:00.

### Using the Project Guide

You can also define a project and set a calendar of working times by using the Project Guide panes. To do this, click the task button on the Project Guide toolbar to display the Project Guide task pane.

The first step is to click the Define the Project link at the top of the task pane. In the Define the Project pane, enter the date that the project work will begin on. Once you have specified a starting date, click the Continue to Step 2 hyperlink at the bottom of the pane.

In this nest stage of the process, make sure that the No radio button is selected (meaning you will not be using Project Server or Project Web Access). (No should be selected by default).

Once you are ready, click the link at the bottom of the pane to continue to step 3.

To define your project, click the Save and Finish link at the bottom of this pane.

When you perform these actions, you will have defined a project. Once you define a project, the Project Guide Tasks pane should be displayed on the left. Now it is time to click the Define General Working Times link.

When you select this link, you will see a calendar showing you the working times corresponding to the calendar template you specify from the drop list on the left. In the image below, the standard calendar has been selected. (You can also choose a 24 hour calendar or a night shift calendar).

After you select your calendar, click the link at the bottom of the pane to continue to step 2.

Step 2 of this process will allow you to choose specific days as working days or non working days. Moreover, you can make adjustments to the working time for individual days by selecting the second (lower) radio button. If you choose the first radio button, you will accept the default working hours shown in the preview calendar on the right.

In the following image, the hours for Monday have been changed to half days by using the drop list controls provided under the second (lower) radio button.

You should notice in the preview calendar that for Monday, only half of the day is highlighted in blue. Since the blue highlighted areas indicate working time for the week, you can see that Mondays are now half-days, with a morning shift of 8:00 to 12:00. If you click the Apply to All Days button, the change you made will be applied to all working days. If you click the link at the bottom of this pane, you will continue on to step 3 of the process.

Step 3 of the Project working time wizard provides a link called Change Working Time.

This link will display the familiar Change Working Time dialogue that we learned about before. You can use this dialogue in the usual way to specify nonworking exception days, or recurring exception days with specific working times.

Once you are finished with this dialogue, click the link at the bottom of the Project Guide pane to proceed to step 4 of the process.

In step 4 of the wizard, you can define your time units. At this point it is best to keep your time units consistent with the calendar that you have designed. If you are using a standard calendar with weekends off and shifts of 8:00 to 5:00 with one hour for lunch, your time units would be 8 hours per day, hours per week, and (on average) 20 days per month.

When you are finished with this step, click the link at the bottom of the pane to continue.

In the final stage of the wizard, you will be asked if you want to define additional calendars. These are for resources that may require a calendar that is different from the base calendar that you created. Don’t worry about additional calendars at this point. For now, just click the Save and Finish link to implement you new calendar.

Lesson 2.2: Creating Tasks

Now that we know how to start a project and define working times, we’re going to start entering project task information. We’ll devote the rest of this section to the key components of a project: the tasks.

A task is particular piece of work, objective, or accomplishment in your project that must be achieved for your project to be successful and complete. For example, to complete our software development we’ll need to test the software. The process of testing is a task, even if we ourselves do not do it.

### Entering New Tasks

By default, Project will open to the task entry screen. Just type your tasks in the list under the heading Task Name.

As you first enter tasks, think of it as brainstorming or as a first draft. Don’t worry about the order, length, start and end times, or other information. Just make a list and we’ll perfect it later!

There is also a Project Guide pane related to entering tasks. You can access this pane by clicking the List the tasks in the project link in the main Project Guide task pane.

Clicking this link will display the following pane.

Here, you have a link to information on tasks, a link to a wizard that will help you import tasks from an Excel spreadsheet, and a check box that will allow you to flag the selected task a milestone. We’ll discuss these options later on.

### Changing a Task’s Duration

You may have noticed that as we entered tasks, Project filled in the duration as 1 day?. The reason for the question mark is because Project entered this information on its own: it guessed.

To change the duration of the task, click in the Duration column for that task and type in the duration. You can use these abbreviations: m for minute, h for hour, d for day, w for week, mo for month, and y for year. So, let’s say that designing the components will take 10 days.

Notice how the Gantt chart (the calendar on the right) changes to reflect the new duration. Also notice that the task will take from January 2, 2007, to January 17, 2007. That’s 15 days, not 10 like we specified! But, Project has consulted our working times, noticed that there are 5 non-working days in that period, and lengthened the task duration as a result. If any other changes are made to the working time, Project will re-calculate all task durations automatically.

If you prefer to use your mouse to make adjustments, you can click and drag the right end of a task’s blue bar with your mouse to extend the duration of a task. You can also use your mouse to drag the end of the blue bar to the left, to decrease the task duration.

You can also use the Start column to change when a task will start. When you change the start date, Project will move the start of the task to the appropriate place on the Gantt chart.

### Moving a Task

If you want to rearrange the position of a task in the list, there are a few ways of doing it. The easiest way is to click the task number to select it. Then, drag it to its new place in the list.

### Inserting a Task

To insert a task, first click to place your cursor at the location that you want the new task. Then, click the Insert menu and click New Task, or press the Insert key on your keyboard.

Now a blank task will appear in the place that you selected. The task that was there before will be pushed down to a lower spot.

### Deleting a Task

To delete a task, first click its number to select it.

Next, click the Edit menu and click Delete Task, or press the Delete key on your keyboard.

When you perform this action, the selected task will be removed.

Lesson 2.3: Editing Tasks

We already explained that when you create a task list, you should create a first draft that can later be modified. In this lesson, we’re going to learn about all sorts of ways to edit tasks!

### The Task Information Dialogue

The Task Information dialogue is where you’ll find most of your task’s information. To open it, double-click a task.

Here’s an overview of the six tabs in this dialogue:

| General | Contains name, duration, percent complete, and dates for the task. |
| --- | --- |
| Predecessor | Enter information about tasks that must be completed before this task can start. |
| Resources | Add resources to the task. |
| Advanced | Set constraints, deadlines, task type, calendar, and earned value method for this task. |
| Notes | Add a note to this task. |
| Custom Fields | Add custom fields to this task. |

Just like with the Project Information dialogue, you can customize task information whenever you want.

### Task Types

Now we are going to take a closer look at the Advanced tab in the Task Information dialogue. This tab contains the settings for task types. You should change this setting whenever possible to maximize Project’s scheduling capabilities.

Let’s define some of the terms that are used when discussing task types.

| Duration | This is how long the task will last. |
| --- | --- |
| Work | The labor needed to complete the task. |
| Units | If a resource is needed to complete the task, how much will be required. |
| Effort-driven | These types of tasks will be completed by people. |
| Material driven | These types of tasks will be completed by resources. |

Here’s an overview of the three task types.

| Task Type | Explanation | If you change… | Project recalculates… | Effort or material driven |
| --- | --- | --- | --- | --- |
| Fixed duration | Duration for these tasks will not change. | Units | Work | Either |
|  |  | Duration | Work |  |
|  |  | Work | Units |  |
| Fixed units (default type) | This task’s units will remain constant. | Units | Duration | Either |
|  |  | Duration | Work |  |
|  |  | Work | Duration |  |
| Fixed Work | This task’s work will remain constant. | Units | Duration | Effort driven |
|  |  | Duration | Units |  |
|  |  | Work | Duration |  |

These task types are based on the simple Project scheduling formula: duration multiplied by units equals work, or work divided by assignment units equals duration. Here’s an example: it will take 100 hours to complete a house:

- Duration=100 hours

- Units= 1 man

- Work= 100 hours

If we add three men, the equation changes.

- Work=100 hours

- Units=4 men

- Duration= 25 hours

This simple equation “duration x units = work” is very important in Project and is the basis for how Project 2007 will establish the relationship between work, units, and task duration.

Task types sound really confusing, but once you start using them they’re easy to understand.

(Note: When we speak of units, we usually are referring to resource units. That means how much of the resource is available. This will be discussed in more detail in the Intermediate manual).

### Setting Milestones

On the Advanced tab of the Task Information dialogue, you’ll also find an option for making the task a milestone.

A milestone indicates a significant event in the project. For our software development project, a milestone might be the completion of the software by the programmers.

A milestone does not have to be based on an existing task. You can create a milestone by double clicking on a blank spot in the task list to invoke the Task Information dialogue. Once you do this, you can click the advanced tab in the dialogue, enter a name for the task in the appropriate field, and put a check in the Mark as Milestone checkbox.

When you create a milestone in this way, it does not require duration, because it is just a marker to indicate a significant point in the project.

Milestones are indicated on the Gantt chart by a diamond shape. In this image you can see a milestone called testing done in position 5 in the task list.

You can add as many milestones as you want in a project.

### Creating Recurring Tasks

Recurring tasks are those that reoccur on a regular basis. For example, you may be meeting with the programmers every two weeks to discuss their progress on the software components.

To create a new recurring task, click to place your cursor in the task list at the point where you want the task to appear. Then, click the Insert menu and click Recurring Task.

Performing this action will display the Recurring Task Information dialogue.

In this dialogue, you will be able to specify the recurring task’s name, its duration, when it recurs, and how long the recurrence will last for. Recurring tasks will have a circular arrow for the task indicator.

You may also notice that the task numbers have changed and that a plus sign appears next to this recurring task. If we click the plus sign, we’ll see that this task actually has 9 parts to it, one part to represent each meeting. This can come in handy for tracking labor.

If you click the minus (-) sign at the top of the recurring task list the recurring tasks will collapse down to one visible entry again.

### Creating Sub Tasks

You’ll find that some tasks have several smaller components that need to be tracked. However, these tasks usually aren’t large enough to require another project file. You can, however, make these tasks subtasks, so that they are connected to the main task. The main task’s duration will reflect all the subtasks.

First, make sure your sub tasks are in the list and that they are underneath the main task. In this example, component testing (testing of each individual component of the software), and integration testing (testing of how the individually tested components work together) are selected to be the subtasks of task 14 (Test the Software).

Next, use the indent button on the formatting toolbar to move the selected sub tasks in one level.

You can now see that Task #14 has a black bar in the Gantt chart and has a minus sign in the task listing. If you click this minus sign, the sub tasks will collapse under the main task.

Project will let you create several levels of tasks, making it possible to have subtasks within subtasks.

### Creating Summary Tasks

As your project progresses, some tasks will become more or less important. You can easily make it a summary task by out-denting it (clicking the left-facing arrow) until the task reaches the level you want. (That is, you can change the level of the task from sub task to summary task.)

Here you can see that Create Testing Plan (task 17) is no longer a sub task of integration testing (task 16).

Notice that Project also automatically changes the Gantt chart, the duration, and start and end dates whenever you change a task’s importance. This makes rescheduling based on priorities easy! You should also be aware of the “Organize tasks into phases” link on the main tasks pane in the Project Guide.

If you click this link, a pane will appear with options for indenting and out-denting tasks, and for adding new tasks.

As is the case with many Microsoft applications, Project 2007 will often provide multiple ways of performing the same basic action (i.e. creating a calendar or adding or indenting a task).

Lesson 2.4: Setting Constraints

Another way to modify tasks is by setting constraints. Constraints restrict the start and finish dates of tasks. In Project 2007, you can add flexible constraints (which are not tied to a specific date) or inflexible constraints (which are tied to a specific date).

### Types of Constraints

In Project, there are eight types of constraints that you can apply to a task.

| Name | Description | Type |
| --- | --- | --- |
| As Soon As Possible (ASAP) | All tasks start as soon as possible if you asked Project to schedule from the start date. | Flexible |
| As Late As Possible (ALAP) | All tasks start as late as possible if you asked Project to schedule from the end date. | Flexible |
| Start No Earlier Than (SNET) | Specifies the earliest possible date that this task can start. | Semi Flexible |
| Finish No Earlier Than (FNET) | Specifies the earliest possible date that this task can finish. | Semi Flexible |
| Start No Later Than (SNLT) | Specifies the latest possible date that this task can start. | Semi Flexible |
| Finish No Later Than (FNLT) | Specifies the latest possible date that this task can finish. | Semi Flexible |
| Must Start On (MSO) | Specifies the date that this task must start on. | Inflexible |
| Must Finish On (MFO) | Specifies the date that this task must finish. | Inflexible |

As you can see, As Soon As Possible (ASAP) is listed in this table as a flexible constraint. This is because there is no specific start date for a task subjected to this constraint. A task with this constraint will start as son as possible with respect to the start of the project. This is the default constraint for tasks scheduled from the Project start date.

On the other hand, the Must Finish On constraint is associated with a hard and fast date that the task must adhere to (the date that the task must finish on). This is an Inflexible constraint.

A constraint like Start No Earlier Than is considered semi flexible. This is because it has a date associated with it, but there is some flexibility associated with how the date is used for scheduling. That is to say, a task with this kind of constraint has the flexibility to start early, as long as it starts no earlier than the specified constraint date.

### Creating a Constraint

You can set constraints in the Advanced tab of the Task Information dialogue box that we looked at in the last lesson.

Notice that the constraint type options are reduced from eight to only three for the task named “Test the software.” This is because this is a summary task (meaning it contains sub tasks). Note that the dialogue’s title even states “Summary Task Information.” You can use the constraint drop lists in this dialogue to set the constraint type and the constraint date for the given task.

When you set a constraint on a task, you will see a calendar icon in the symbol field next to the task. If you let your mouse pointer hover over the icon, you will see a comment box open with a brief description of the constraint. .

In Project, it is possible to impose a constraint on a task by dragging the blue task bar in the Gantt chart. For example, notice the position of the task named Build Components in the Gantt chart shown below.

Now, we will drag the blue bar (which represents the task’s duration) in the Gantt chart towards the right using the mouse. .

You should notice that the bar has grown longer because it now overlaps three non working days, increasing its length with respect to the time line. Also, you will notice a calendar icon representing a “Start no earlier than” constraint in the symbol field next to the task name. This is because the task has been moved down the time line away from the project start date, which was also the task’s original start date.

### Setting Task Deadlines

You can also use the Advanced tab in the Task information dialogue to set a deadline for a particular task.

To set a deadline, simply use the deadline drop list (or enter a date directly) to specify the date that this task needs to be completed by.

If you apply a deadline to a task, and the task’s duration takes it past the deadline date, you will see a red diamond with an exclamation mark in it beside the task symbol field beside the name.

You will also see a white arrow indicating the deadline in the Gantt chart to the right of the task.

### Constraints versus Deadlines

Constraints and deadlines may seem similar, but they’re used for very different purposes. Constraints will actually constrain the task’s scheduling. Deadlines will not constrain a task in the same way, but they will display a visual marker telling you that the deadline has been missed.

Here’s a summary of how they differ.

| Constraints… | Deadlines… |
| --- | --- |
| Affect how Project will schedule time and resources, sometimes limiting scheduling capabilities | Do not affect Project’s scheduling |
| Have multiple types | Have limited settings |
| Can be updated at any time | Can be updated at any time |
| Only certain types can be applied to summary tasks | Can always be applied to summary tasks |

In general, it is a good idea to be careful when using constraints. Remember to be conscious of how constraints may limit Project’s scheduling capabilities.

There is also a Project Guide task pane available for adding deadlines and constraints.

This pane can be displayed by clicking the “Set deadlines and constrain tasks” hyperlink on the main Project Guide Tasks pane. Remember, Project often provides multiple options for using a given tool.

Section 2: Review Questions

- In MS Project, the main parts of a typical project are referred to as…

- Components

- Tasks

- Modules

- None of the above

- Which of the following is true?

- Project 2007 is only used for large projects

- You must have all of your tasks laid out in order before you enter them

- All tasks need to have the correct duration when they are entered into Project

- You can pretty much enter Tasks into project as you require, and then organize them later

- You can move a task by …

- Using the Move button on the standard toolbar

- Clicking and dragging it

- Using the Move menu options

- All of the above

- Which of the following is not a valid task type?

- Fixed Units

- Fixed Duration

- Fixed Work

- Fixed Management

- What is the basic equation that Project uses to evaluate and schedule tasks?

- Units x Duration = Work

- Units – Critical Length =Duration

- Duration – Work = Units

- Any of the above

- What is a Milestone?

- A type of critical path

- A type of calendar

- A marker for a particular stage of a project

- None of the above

- A summary task is…

- A task that contains associated sub tasks

- A task that is always critical

- Any task with a special calendar

- All of the above

- What are three types of constraints?

- Flexible, semi flexible, and inflexible

- Flexible, critical, and summary

- Units, Effort, and working days

- None of the above

- A deadline is…

- A date that the task must be completed by

- A date that the task must be completed after

- A date the task will hopefully be finished by

- An inflexible constraint

- A recurring task will recur…

- As often as you specify

- Only once

- A maximum of 3 times

- A minimum of five times

Section 3: Scheduling a Project

In this section you will learn how to:

- Use calendar types

- Set up a calendar

- Create a new calendar

- Change calendar views

- Adjust the time scale

- Save a baseline

- View a baseline

- Clear a baseline

- Save an interim plan

- Clear an interim plan

- Use critical paths

- Find, view, and shorten the critical path

Lesson 3.1: Creating the Project Calendar

One of the first things you learned about setting up a basic project was how to make changes to the project calendar. In this lesson, we’re going to take a closer look at how to set Project’s calendars. Calendars are an important concept in Project 2007 because they will be used as the foundation for how the Project program schedules your tasks. Keep in mind that it is important to be as accurate as possible when setting up your calendar. If your calendar setup is off, your project scheduling will likely be incorrect as well.

### Calendar Types

There are three main entities in Project 2007 that calendars can be associated with: Projects, Resources, and Tasks.

| Project calendar | This is the main calendar that controls the default scheduling for all tasks in a project. |
| --- | --- |
| Resource calendar | Each resource can have its own calendar to reflect its hours of availability. |
| Task calendar | Sometimes a task will need to have its own calendar to reflect its duration, especially if the task is performed during nonworking time. (For example, a machine that works on a task may run on weekends or 24 hours a day, where a person would not.) |

There are also base calendars, which can be thought of as templates that the calendars mentioned above can be based on. These base calendar types are:

| Standard | Working time is set Monday through Friday, 8 am to 5 pm, with an hour (noon to 1 pm) set aside for lunch. |
| --- | --- |
| Night Shift | Working time is set Monday through Friday, 11 pm to 8 am, with an hour (3 am to 4 am) set aside for lunch. |
| 24 hours | Working time is every day and hour of the week; useful for resources (such as machines) that run constantly. |

Project schedules tasks and resources by using the Project, Resource, and Task calendars in the following way. If a task does not have any resources and there is no task calendar, it is scheduled according to the Project calendar. If a task does have resources assigned to it and there is no task calendar, then the resource calendar will be used for scheduling. If a task does have a task calendar, it (the task calendar) will be used for scheduling.

### Setting up the Calendar

Several lessons ago, we learned how to set up the project calendar. We clicked on the Tools menu and clicked the Change Working Time option, and this dialogue appeared:

This calendar allows you to set working or nonworking times for particular week days (for example, every Friday) or dates (for example, August 7) on any month. You can also adjust the amount of working time/hours for a particular day.

In addition, you can click the Options button to change the default start and end time (Daily) as well as the number of hours per day, week, and month.

You will also recall that you can use the Project Guide task panes to set up a calendar.

### Creating a New Calendar

If you have different teams of employees/resources working on different shifts, you may want to consider using multiple calendars. To create a new calendar, open the Change Working Time dialogue and then click the Create New Calendar button.

This action will display the New Base Calendar dialogue.

In this dialogue you can enter a name for your calendar and choose to either create a brand-new calendar or make a copy of one of the existing calendars available in the calendar drop list.

If you have not already created any calendars at this point, the options in the drop list will only consist of the three base calendar types (Standard, Night Shift, and 24 Hour). If you have already created additional calendars, these calendars will also be available in the drop list for you to select.

Once you click OK in the lower right, the calendar you created will be available for selection in the top of the Change Working Time dialogue box.

Now, you can specify the working days, nonworking days, and exceptions for the new calendar by using the options in the dialogue.

You should also remember that if you use the Project guide task panes to create your initial project calendar (see Lesson 2.1) there is a pane in the Project Working Times wizard that will allow you to create additional calendars.

### Using Calendar View

If you wish, you can change the view of your Gantt chart and tasks to a monthly Calendar view. To do this, just click the View menu and then click the Calendar option.

When you select this calendar option, a monthly calendar will be displayed in the working area of your screen in a large, easy to read format.

Notice that your tasks, their durations, and working and nonworking days are visible on the calendar. If you let your mouse pointer hover over a task in the calendar view, any constraint that the task has will appear in a small comment box.

### Adjusting the Timescale

So far, we have been working with the task entry/Gantt chart view. As you know, the Gantt chart view shows a timeline of the tasks in your project.

By default, the timeline at the top shows two tiers: weeks and then days.

You can change this view by clicking the Format menu followed by the Timescale option.

When you choose this option, you will see the following dialogue box.

The options in this Timescale dialogue allow you show up to three tiers. You can control how many tiers are shown, how each tier appears and how non-working time appears.

Here is a three tier timescale with quarters on the top tier, months on the middle tier, and weeks on the bottom.

Here is a three tier timescale with months on the top, weeks in the middle, and days on the bottom. Also, the non-working time has been altered so that it is displayed in yellow.

Finally, here is a two tier timescale with hours on top and minutes on the bottom. The-non working times are shown in yellow. (Notice how the blue task bars stretch out because of the different time scale.)

These timescale customizations are great for adapting your view to short term or long duration projects.

Lesson 3.2: Setting a Project Baseline

In Microsoft Project 2007, a baseline is a snapshot of the project’s tasks, milestones, resources, and assignments at a given point. These fields will remain static in the baseline to give you a point against which your project’s progress can be measured and tracked.

Once your project is underway, you can see the progress of your project against the saved baseline by using the Tracking Gantt view under the View menu.

### Baseline Basics

Here is a breakdown of regular fields that Project captures when you save a baseline.

| Tasks | Duration |
| --- | --- |
|  | Start |
|  | Finish |
|  | Work |
|  | Cost |
| Assignments | Start |
|  | Finish |
|  | Work |
|  | Cost |
| Resources | Work |
|  | Cost |

For tasks, assignments, and resources, Project records the baseline work and cost over time. This can help you see patterns, trends, and variances.

### Saving a Baseline

Once you have planned and laid out the tasks, resources, and scheduling for your project. It is a good idea to save a baseline before work on the project proceeds.

There are two methods you can use to save a baseline. The easiest is to click the drop-down arrow next to Track on the Project Guide and choose “Save a baseline plan to compare with later versions.”

Next, you can click the Save Baseline button in the Tracking task pane that will appear on the left of the screen. This will save a project baseline.

(Note: This procedure will save the baseline as a project baseline unless you have specific tasks selected in the task entry area on the right. If you do have tasks selected, you will be given the option of saving a baseline for the selected tasks only.)

Alternatively, you can also click the Tools menu, choose Tracking, and click Set Baseline.

This action will display the Set Baseline dialogue box.

You can see from this dialogue that Project lets you save a baseline for the entire project or for selected tasks only by choosing the appropriate radio button. (Remember, if you are setting a baseline for specific tasks, you must select the tasks in the task entry area before you set the baseline). As you can see from the drop-down list menu under the Set Baseline radio button, Project 2007 will allow you to save up to 11 baselines.

Once your options are set, click the OK button to save the baseline. When you click OK, Project 2007 will save a snapshot of the information for this project.

### Viewing a Baseline

To view your baseline, right-click on the cell that is in the top left hand corner of the task entry sheet.

When the pop up menu appears, click the More Tables option to display the More Tables dialogue.

Alternatively, you can choose the View menu, followed by the Table: option, followed by the More Tables option.

Here is the More Tables dialogue.

At the top of the dialogue, choose whether you want to see a task or a resource baseline. (Since we haven’t yet discussed resources, we’ll stick with tasks.) Next, choose Baseline from the list and click Apply.

This view may look the same as the task entry view, but take a close look at the column headers. You will notice that we are now viewing the baseline duration and start dates, rather than the current ones.

To go back to the regular view, right-click on the top left-hand cell and choose Entry.

If you click the View menu and then click the Tracking Gantt option, you will see the current progress of the project measured against the baseline.

You will notice grey bars (the baseline) tracking along underneath red bars (current progress of the project). In this example, the project has not been started yet, so there is no difference between the baseline and the current progress.

Progress tracking will be dealt with in greater detail in the Advanced manual.

### Clearing a Baseline

If you would like to clear an existing baseline, click the Tools menu, choose Tracking, and click Clear Baseline.

This action will display the Clear Baseline dialogue.

To clear (remove) a baseline, just select it from the drop list and click the OK button.

Lesson 3.3: Setting an Interim Plan

You may have noticed that there was another set of options in the Set Baseline and Clear Baseline dialogue boxes. These options are for interim plans, which are similar to baselines.

Like baselines, an interim plan is a snapshot of your project at different points. However, interim plans only save the start and finish dates for current tasks. They do not keep all the information about tasks and assignments that are contained in a baseline.

Interim plans can be used to track your progress and to compare with a baseline plan or your current situation. Interim plans are best used for planning stages of your project, while baselines are more appropriate for a larger scope of project execution and tracking.

### Setting an Interim Plan

Setting an interim plan is a lot like setting a baseline plan: click the Tools menu, choose Tracking, and click Set Baseline.

When the dialogue appears, select the Set Interim Plan radio button, set up your options, and then click the OK button.

You can use the Copy or Into menus to copy particular start/finish dates or particular baselines into other start/finish dates or baselines. (Start/Finish represents the default start and finish fields for each task, while Start1/Finish1 through Start10/Finish10 are custom fields, which we have not talked about yet.)

As with baselines, you can save an interim plan for one or more selected tasks, or for the entire project (all of the tasks). In the image shown above, an interim plan is being set for the entire project.

When you are finished configuring the options, click the OK button to create the interim plan.

### Viewing an Interim Plan

Unlike baselines, there is no easy way to view interim plans. To view an interim plan, you must add custom fields to the task sheet view. This is an exercise that we’ll save for later.

### Clearing an Interim Plan

Clearing an interim plan is just like clearing a baseline plan: click the Tools menu, click Tracking, and click Clear Baseline.

When the Clear Baseline dialogue appears, select The Clear Interim Plan radio button, and then choose the plan that you want to clear from the drop list.

Once you are ready, click the OK button to clear the selected plan.

Lesson 3.4: Setting the Critical Path

The next planning element we’re going to look at is your project’s critical path. The term critical path certainly sounds important. What is a critical path, you ask? And how does Project make one? The answers to these questions will serve as the topics for this lesson.

### What is the Critical Path?

There are a couple different ways to describe a critical path. A project’s critical path can be said to consist of the tasks that are crucial for a project’s completion. A critical task is a task that cannot be delayed with out affecting the project finish date unless the duration of another critical task is shortened to compensate. For the project to be completed on schedule, the tasks that comprise the critical path must be completed on schedule. Tasks on the critical path are essential components of the project and are therefore not optional.

For example, your software development project could survive on schedule if you miss or delay a meeting with the programmers. However, if the components are not developed or tested according to schedule, the project will have to be delayed.

In other words, the task of building the software components and the task of testing the software components are critical tasks. The meetings with the programmers are not.

Because the critical path is composed of the essential components for your project, and because your project cannot be completed until all of the tasks on the critical path are completed, the duration of the critical path represents the shortest possible time span that your project can be completed by.

### How Does Project Determine a Critical Path?

Project determines a critical path based primarily on the constraints that are applied to tasks. In a basic sense, if a task has an inflexible constraint it is deemed critical. If a task has a flexible constraint, it is not a critical task, as the task allows some slack for adjustment if required. If you change the constraint type for a task, the critical status of the given task will change correspondingly.

One way of thinking of critical tasks is to consider the earliest finish time for the task, and the latest finish time for that same task. A task’s finish time can be a function of its duration, its constraints, and its dependencies on other tasks.

If a task’s earliest possible finish time is different from its latest possible finish time, it has some slack (wiggle room) and is not considered a critical task.

However, if a task’s earliest possible finish time is the same date as its latest possible finish time, there is no leeway. This kind of task is critical and will be a component of the critical path.

### Viewing the Critical Path

The easiest way to view your critical path is to select to click the Report menu on the Project guide task bar, and then choose “See the Project’s critical tasks.”

This will display the following Project Guide pane and the critical path for the project in the Gantt chart to the right.

Notice that you can use the “Apply a filter” drop list in the Critical Path pane to filter the tasks.

If you want more control over how to view your project’s critical path, use the Gantt Chart Wizard. Just remember when you use the wizard or the guide pane to view the critical path, the changes cannot be undone, so make sure that you save your project before viewing the critical path.

To launch the Gantt Chart Wizard, click the wizard button () on the formatting toolbar.

In the first Wizard box, click the Next button.

In the next dialogue box that appears, you can choose to view your project’s critical path. (Note that you can also view the baseline, too.) Or, you can use the Other menu to choose a special style for your critical path.

In the next dialogue, you can specify the task information that will be displayed in your Gantt chart.

In this example, dates will be shown with the critical path. When you click the Next button, a dialogue appears to let you choose whether or not task dependencies (which we have not covered yet) are shown.

An example of a task dependency is when a task cannot begin unless a previous task is completed. (For example, you cannot test a computer program until it has been written.)

In the final Wizard box, you can click the Format It button to apply the changes.

At any time (before you click Format It), you can move back through the earlier stages of the wizard by clicking the Back button.

Once you click the Format It option, critical tasks will appear different in the Gantt chart, as compared to regular tasks.

In this example image, the critical tasks are shaded in red, while the non critical tasks are shaded in blue.

### Shortening the Critical Path

If you have a long term project that is going to cost a lot, you may want to shorten the critical path, which will thereby shorten the length of the whole project.

There are a number of ways to shorten the critical path which may or may not be feasible depending on the particular details of a given project. These ways include:

- Shortening the duration of a critical task

- Change a critical task’s inflexible constraint to flexible one

- Dedicate additional resources to work on a critical task (a way of shortening its duration)

- Re-think task dependencies (Are there parts of a task that can be broken off into smaller tasks and completed in parallel with other tasks?)

- Schedule overtime work for a task (allow the resources to work longer hours)

Let’s take the following critical path as an example.

Here, the critical path (shaded in red) goes from 8/10 (August 10) to 9/4 (September 4). You will also notice from the yellow comment box that the last critical task has a Start no Earlier Than constraint set to August 22 (8/22).

If we change this constraint to an earlier date (like 8/21) the critical path will be shortened.

In this image, you can see that the constraint date has been changed to no earlier than 8/21. Now the critical path (and project) are completed on a Friday instead of the following Monday.

There will be more discussion of adding resources to a task, scheduling overtime, and changing the relationships between tasks in the Intermediate level manual.

Section 3: Review Questions

- Which of the following is not a valid calendar type in Project?

- Standard

- 24 hour

- Night shift

- Split Shift

- If you increase the time scale in your project, (from months/weeks to days/hours)…

- Your Gantt bars will seen longer

- Your Gantt bars will seem shorter

- Your Gant bars will not change

- You cannot change the time scale

- A baseline is used to …

- Calculate units based on effort

- Track progress

- Create a calendar template

- Summarize critical tasks

- Which of the following is false?

- You can create multiple baselines in Project

- You can clear unwanted baselines

- You cannot specify baselines for selected tasks

- You can set a baseline for an entire project

- The duration of a project can never be shorter than…

- The critical path

- The sum of the task durations

- The sum of the durations for the longest tasks

- Any of the above

- You can view the critical path by using…

- The report menu

- The Gantt chart wizard

- A and B

- None of the above

- A critical path is composed of…

- The longest tasks

- The shortest tasks

- The critical tasks

- All of the above

- You can shorten a critical path by…

- Assigning more resources to it

- Assigning a different schedule to it

- Changing the constraints

- All of the above

- When you create a new calendar you must …

- Use the Standard calendar

- Use the 24 hour calendar

- Use the Night Shift calendar

- None of the above

- A baseline is exactly the same as an interim plan.

- True

- False

- It depends

- All of the above

Section 4: Printing and Viewing a Project

In this section you will learn how to:

- Check spelling

- Select text

- Use cut, copy, and paste

- Use Undo and Redo

- Insert page breaks

- Use Zoom

- Use the View bar

- Use basic views

- Use advanced views

- Use the Find dialogue

- Set page options

- Set margins

- Set headers

- Set footers

- Modify the legend

- Change the view settings

- Open Print Preview

- Use Print Preview

- Use Print commands

- Use the Print dialogue

Lesson 4.1: Basic Editing Tasks

Now that you know how to create a basic project layout, it is time to learn how to prepare and finalize it so copies can be printed for your managers or co workers. Many of the editing and finishing tools in Project 2007 will be familiar to you if you have already used other Microsoft Office programs.

### Checking Spelling

If anyone else but you is going to see your project, you should make sure to check it for spelling mistakes. There are three ways you can start a spell check:

Press the F7 key on your keyboard

Click the spelling button () on the standard toolbar

Click the Tools menu and click Spelling

(Note: If the spelling button is not available on the toolbar, click the small arrow at the end of the toolbar to display the available buttons.)

Once you perform any of the commands from this table, you’ll see the following dialogue:

This box will display the first incorrect word (a word not in the dictionary) that Project 2007 finds. You can choose a suggested spelling from the Suggestions list and click Change to correct the mistake with the selected alternative. If the mistake occurs more than once, you can click the Change All button to correct all instances of the mistake.

If you wish, you can click Ignore or Ignore All to leave the original spelling error unchanged. Project will then move onto the next incorrect word, and the next, until all mistakes have been addressed.

Keep in mind that Project 2007 doesn’t check grammar, only spelling. The spell checker checks words in the project against a pre-defined word list (called a dictionary). If you enter a correctly spelled term that is not in the dictionary, Project 2007 will consider it to be incorrect.

### Selecting Text

When you select text, you are identifying it (highlighting it in black or blue). Editing and formatting options can then be applied to the selected text as a whole. When you select a row in a task entry area, you can reposition or remove the task, or copy it to the clipboard

In Project, to select a row, simply click the row header (the cell at the left of the row).

The selected row will be highlighted in black.

To select some individual text, click in a cell that contains the text that you want to select. When you do this, the cell will be surrounded by a thick black border.

When you see this border, click inside the cell again, so that your cursor is flashing inside it.

Now you can use your mouse to click and drag over the text that you want to select.

When you select text in this way, any font or formatting options that you choose will be applied to the selected text. If you hit your delete key, the selected text will be removed.

### Cutting, Copying, and Pasting

Once your text is selected, what can you do with it? Well, you can cut, copy, or paste it into another location.

| Cutting text | Removes it from your document and places it on a storage area called the clipboard. |
| --- | --- |
|  | To cut text, selecting the text or cells, then click the Edit menu followed by Cut. You can also use the Cut button () on the standard toolbar, or use the Ctrl + X shortcut. |
| Copying text | Leaves it in your document, but also places in on the clipboard. |
|  | This lets you copy frequently used phrases and other items so they can be placed in different parts of your project. |
|  | Copy text by selecting it, then clicking the Edit menu and clicking Copy. You can also use the Copy button on the standard toolbar () or use the Ctrl + C shortcut. |
| Pasting text | Places the last item you cut or copied (and is now on your clipboard) into your project at the location of your cursor. |
|  | Click where you want to put the data in your document and then, click the Edit menu and click Paste. You can also use the Paste button () on the standard toolbar, or use the Ctrl + V shortcut. |

You can also cut, copy, and paste entire cells if you wish. The process is pretty much the same: select the cell (by clicking on it), and then use a cut or copy command. Then, click in the location where you want the information to be placed, and click Paste.

### Using Undo and Redo

If you perform an action and you don’t like the results, click the Undo arrow () on the standard toolbar. This will reverse your last action. (You can also click the Edit menu and click Undo, or press Ctrl and Z.)

Before Project 2007, Project did not retain a list of actions. As soon as you used the undo feature, the Undo arrow turned into a Redo arrow. This only allowed you to undo a single action (the last one you performed). In Project 2007, a history of the actions that you performed is kept. This means that in Project 2007 you can use undo several times to reverse a series of pervious actions.

If you click on the small arrow next to the undo button, you will see a list of the actions that you can undo.

You can click the Undo button repeatedly to reverse your recent actions one at a time, or you can select an adjacent group of actions from the list with your mouse (so long as the selection includes the most recent action). When you select a group of recent actions, they will be undone at once.

When you click the Redo button () you will be able to redo actions that have been undone. You can click the redo button repeatedly to redo actions one at a time, or you can click the small arrow beside the redo button and select multiple actions to redo from a list.

Note: There are some actions that cannot be undone or redone, such as using the Gantt Chart Wizard and saving a file. In these cases, the Undo and Redo commands will be unavailable.

### Inserting Page Breaks

Another neat editing feature at you disposal is the ability to insert page breaks. This can come in handy if you’re planning to print out a task list or a calendar, so that your data fits neatly onto the pages.

To insert a page break, click to place the cursor at the spot that you want the new page to start. Next, click the Insert menu and then click Page Break.

Now, your page break will appear as a dotted line.

To remove a page break, place your cursor in the cell below the break. Then, click the Insert menu and click Remove Page Break.

If your task or resource list is very long, Project may automatically insert page breaks for you. When this happens, these breaks cannot be removed.

Lesson 4.2: Changing Your View

One of the major benefits of using Project as a management tool is the variety of view capabilities that are available. You can easily display your data in dozens of ways, depending on what information you want to present and how you want to present it. In this lesson, we’ll learn about some of Project’s basic view tools.

### Using Zoom

The Zoom tool lets you get a close-up (detailed) or a faraway (big picture) look at your project. The easiest way to zoom is to use the zoom in () and zoom out () buttons on the standard toolbar. When you use these buttons, you will change the scale of the timeframe being displayed.

Here is the Gantt chart screen at the default Zoom setting. The top tier of the timescale represents weeks, and the bottom tier represents days.

Here is the same screen after clicking the Zoom In button. You will notice that the top tier of the time scale is now days, and the lower tier is blocks of six hours each.

If you need a more precise zoom tool, click the View menu and click Zoom.

This action will display the zoom dialogue box.

Here, you can choose a pre-defined zoom level (by clicking a radio button) or set a custom level (with the custom drop list). Once you click OK, your settings will be applied.

Here is an example of the Entire Project zoom level.

Even if you’re using a custom zoom level, the Zoom In and Zoom Out buttons on the standard toolbar are still available.

### Using the View Bar

The View Bar gives you easy access to Project’s basic views. To display it, click the View menu and click View Bar.

Performing this action will display a new vertical toolbar on the left hand side of the screen.

Here’s a basic overview of each view available on the view bar. We’ll get into each view in depth in the Intermediate lessons.

| Calendar | Displays a monthly calendar with tasks. |
| --- | --- |
| Gantt Chart | Default view; shows a timeline of tasks and resources. |
| Network Diagram | Shows how tasks and resources are interconnected. |
| Task usage | View a task’s duration and the actual work. |
| Tracking Gantt | A timeline of task durations and actual work. |
| Resource Graph | A graph that shows how much resources have been used. |
| Resource Sheet | A table used to enter resources. |
| Resource Usage | View a resource’s actual work. |

To hide the View Bar, just click the View menu again and click the View Bar option.

### Using Basic Views

You can always access Project’s basic views from the View menu. Simply click the View menu and then click the view you want, placing a check next to it.

In the image above, the Gantt chart view is selected.

### Using Advanced Views

If Project’s basic views aren’t what you are looking for, click More Views on the View menu or the View Bar.

When you choose either of these options, you will display the More Views dialogue.

This dialogue contains all the basic views, plus these additional views:

| Bar Rollup | Gantt chart view that groups summary and sub tasks. |
| --- | --- |
| Descriptive Network Diagram | Similar to Network Diagram, but provides more details. |
| Detail Gantt | Gantt chart view that shows details about task slack/slips. |
| Leveling Gantt | Similar to Task Entry view, but tasks and their allocated resources are shown graphically. |
| Milestone Date Rollup | When used after running the rollup_formatting macro, shows subtasks as milestones. Subtasks are grouped with their summary tasks and marked with the name and start date. |
| Milestone Rollup | When used after running the rollup_formatting macro, shows subtasks as milestones. Subtasks are grouped with their summary tasks and marked with the start date. |
| Multiple Baselines Gantt | Shows your first three baselines. |
| Relationship Diagram | Similar to Network Diagram, but shows only one task and its linked tasks. |
| Resource Allocation | Shows the Resource Usage view in the top pane and Leveling Gantt in the bottom pane. |
| Resource Form | Displays detailed information about one resource. |
| Resource Name Form | A simplified version of the Resource Form. |
| Task Details Form | A detailed version of the Task Entry sheet that focuses on one task at a time. |
| Task Form | Displays detailed information about one task. |
| Task Name Form | A simplified version of the Task Form. |

We’ll cover all of these views in more detail in the Intermediate lessons.

### Using the Find Dialogue

The last view tool that we’re going to talk about is the Find dialogue. To open it, click the Edit menu and click Find. You can also use the Ctrl + F keyboard shortcut.

When the dialogue appears, you can type in a word or term that you are searching for, and specify where Project should look. Click Find Next, and Project will highlight the next instance of the word.

If you expand the Test drop list, you will see a list of conditions that you can apply to your search criteria. You can also specify if the case (capitalization) will be a factor in the search.

In the example above, entries in the Name field will be searched, and those entries that do not contain the term Test will be found in sequence as you click the Find Next button.

In this example, items in the Name field are searched and the ones that contain Test will be found.

You can also click the Replace button to replace your search term with a particular word. (This feature is not available in all views.)

Once the information is entered, you can use the Replace, Replace All, and Find Next buttons to perform the corresponding actions. Once you’re finished finding and replacing, click Close.

Lesson 4.3: Using Page Setup

Many people use Microsoft Project 2007 for its report generation and printing capabilities. Although the default settings are usually sufficient, you may need to customize margins, headers and footers, the legend, or other page options.

All of these settings can be controlled from the Page Setup dialogue, which is accessible by clicking the File menu and clicking Page Setup. Keep in mind, that everything you set up here is set on a per-project basis, so you can choose whatever settings you want without affecting your other Project files.

### Setting Page Options

The Page tab of the Page Setup dialogue lets you control page orientation, scaling, and paper size.

From the Paper Size drop list you can choose from a wide variety of size options including letter, legal, executive, envelope, and index card. If you click the Print Preview button, you can see a preview of how you page option settings will look when printed.

### Setting Margins

The Margins tab lets you control margins and page borders. There’s also a preview box so you can see how your margin settings will look.

You can adjust the various margins by using the small arrows to incrementally change the margins, or by entering margin values directly into the fields provided.

You can also specify if you want borders around every page by selecting the appropriate radio button. You will also notice the Print Preview  and Options buttons that are available on every tab in the Page Setup dialogue.

### Setting Headers

The Header tab lets you specify information that will be included at the top of every printed page.

Set your options using the features at the bottom of the screen and you’ll see a preview in the Preview area above. (To use these options, select an item that you want to include from the General or Project Fields drop list, and then click the corresponding Add button.)

You can also use the button list (bordered in red above) to insert dynamic fields into your headers. You can use these buttons to insert page numbers, the current date, the current time, and more into your header.

As an example, look at the dialogue presented in the following image.

In the Alignment view area, you can see that the date, time, and project title have been added to the header. (&[Date] &[Time] &[Project Title])

If you click in this Alignment area, your cursor will appear there, and you can delete or edit these entries. The presentation of the items in the Alignment area will be previewed in the Preview area. This preview shows what your header will look like.

### Setting Footers

The Footers tab has the same features. The difference is that this text will be placed at the bottom of every page.

### Modifying the Legend

If you have used Microsoft Project 2007 to create a chart (such as a Gantt chart) or a diagram, or graph, you may want to modify the legend (which describes the various chart or graph elements) using the options on the Legend tab.

Notice that you can also specify with radio buttons if you want the legend on a separate legend page, or on every page. There is also a Legend Labels button which you can use to format the font size and other qualities of the legend labels.

If you use the same controls that appear in the header and footer tab to add elements to the legend, these added elements will appear on your printout in the area with the legend symbols.

The following image is a print preview screen with the legend shown on the bottom of the page beneath the diagram, inside the large red rectangle.

### View Settings

The View tab in the Page Setup dialogue box contains options for printing a specified number of sheet columns, as well as options for printing notes, fitting the timescale to the printed page and more.

In this tab, you select the options you want by placing check marks next to them.

You will notice in the image above that the bottom two options are not available. The options that are available in the view tab will depend on the type of chart, diagram, or graph that you are printing.

No matter what tab in the Page Setup dialogue you are working with, if you click the Print Preview button, you will get an idea of what your pages will look like in the Print Preview screen. From the Print Preview screen, you can click the Page Setup button to return to the Page Setup dialogue.

Lesson 4.4: Printing a Project

Now that you know how to create, finalize, and set up a project, it is time to learn how to print it!

### Opening Print Preview

Before you print your project, you should get an idea of how it will look on paper. To do this, click the File menu and click Print Preview.

As mentioned previously, you can also display the Print Preview screen from the Page Setup dialogue.

### Using Print Preview

Once you invoke Print Preview, you will see a screen that presents a preview of you’re your current project screen will look like when printed. As an example, here is a Project screen:

Now, the following image shows the Print Preview screen for the same project as shown above.

This is how the information currently displayed in Project will appear on paper.

You can use the arrows at the top of the screen to move through the printed pages, and you can use the layout buttons (shown in the red border) to change your view.

You can also open the Page Setup dialogue right from this window, using the Page Setup button next to the toolbar. Once you’re done with Print Preview, click the Close button to make the screen disappear.

### Using Print Commands

If you’re in the main Project window, you can use any of the following commands to print your project:

File – Print

Ctrl + P

Print icon () on the standard toolbar

You will also find Print commands in the Print Preview screen  and in the Page Setup dialogue.

### Using the Print Dialogue

When you perform the File - Print command, or use the Ctrl + P shortcut, or click the Print button in the Print Preview screen or the Page Setup dialogue, you’ll see the following Print dialogue:

In this dialogue, you can choose the printer that you want to use, specify a particular page or page range to be printed, change what portion of the project is printed, and specify the number of copies to be printed. You can also choose to ignore manual page breaks by clearing the “Manual page breaks” check box.

Once your options are set, click OK to print your project!

### Using the Project Guide to Print your Project

The Project Guide print wizard can help you print your control the printing of your project with an easy to use, step by step format. To start the wizard, click the down arrow next to Reports on the Project Guide toolbar and click Print Current View as a Report.

When you perform this action, you will invoke the Project Guide print wizard. In the first pane of the wizard, choose a radio button to print one page or multiple pages.

In the next stage of the wizard, you can select what component of the report that you want to change.

Depending on your selection, you will be provided with a link to the appropriate tools in the Page Setup dialogue to accomplish the task.

In the next stage of the wizard, you can choose to set up Header, Footer, or Legend. Depending on your selection (from the radio buttons), you will be linked to the appropriate controls in the Page Setup dialogue.

Finally, in the fourth and final stage of the wizard, you can choose from a number of modifications.

Depending on your choice, you will be provided with a Page Setup link to the appropriate controls.

You should notice that you can open Print Preview or print the project from the pane at any time. You can also click Done at any time to exit the wizard and save your changes.

Section 4: Review Questions

- Which of the following are valid ways of moving a task?

- Dragging with the mouse

- Copying and pasting

- Cutting and pasting

- All of the above

- Which of the following is not a valid print command?

- Ctrl + P

- File - Print

- Printer icon on the toolbar

- Typing Print in the command dialogue

- Which of the following is a Gantt chart view that groups summary and sub tasks?

- Relationship diagram

- Network Diagram

- Bar Rollup

- Resource form

- Print Preview can be opened from…

- The File menu

- The Page Setup dialogue

- The Project Guide print wizard

- Any of the above

- Which of the following statements is false?

- You can specify your own page breaks in Project 2007

- You can adjust the page margins in the Page Setup dialogue

- You can only undo your last action in Project 2007

- You can add footers and headers to your printed pages if you wish

- You can use the Print dialogue to…

- Specify the number of copies to print

- Specify which printer to use

- Specify the size of the page

- All of the above

- You can access the Page Setup dialogue from…

- The Print Preview window

- The File menu

- The Page Setup button on the formatting toolbar

- A and B

- When you use the Zoom feature…

- The time scale will change

- The critical path will shorten

- The duration of a task will shorten

- None of the above

- You can display the view bar by…

- Clicking the Display View Bar button on the formatting toolbar

- View - View Bar

- File - View Bar

- None of the above

- If you click the Redo button you will…

- Clear the clip board

- Redo the last action

- Redo the last action that was undone

- None of the above

Index

Baseline	98, 99, 101, 102, 104, 106, 107, 109, 114, 118, 119

Clearing	106

Fields captured	98

Saving complete	99

Saving for select tasks	99

Saving via Project Guide	99

Saving via Tools menu	100

Set Baseline dialogue box	101

Viewing	102, 104

Viewing in Tracking Gantt	105

What is?	98

Calendar

And Project scheduling	88

Base	88

Change Working Time	51, 61, 89, 91, 92

Creating new via Change Working Time dialogue	91

Creating via Project Guide	91, 93

Defining working times via Project Guide	59

Effective dates	5

Exception dates	5, 52

Legend	52

Recurrence and Exception Dates	55

Setting default times	90

Types	88

Using calendar view	93

Change Highlighting	4

Constraints

Creating via Gantt chart	81

Creating via Project Guide	84

Creating via Task Information	80

Indicators for	81

Types	79

Vs. deadlines	83

Critical Path	85, 111, 112, 113, 114, 116, 118, 119, 154

And critical tasks	111

Determining	111

Formatting	114

Shortening	116

Viewing	112

What is?	111

Dialogue Boxes	15

Editing Commands

Copying	123

Cutting	123

Deleting text	123

Multilevel undo	4, 124

Pasting	124

Redo	125

Selecting cells	122

Selecting text	122

Spellcheck	121

Undo	124

Using find	134

Using replace	136

Entering Project Information	49, 50, 69

Files

Closing	33

Opening	27

Opening multiple	32

Re-saving	31

Saving	30

Gantt Chart	10, 66, 73, 76, 77, 81, 83, 93, 95, 112, 114, 115, 118, 127, 132, 133, 142, 153

Gantt Chart Wizard	24, 113, 125

Help Features

Help menu overview	34

Help via Dialogue Box	42

Help window	35

Navigating help window	37

Offline help	39

Online help	36

Table of contents	38

Type a Question	9, 40

Interim Plans	107, 108, 109, 119

Clearing	109

Saving	107

Saving for selected tasks	108

Viewing	108

Menus

Help	34

Overview	20

Right-Click	12

View	132

What are?	9

Microsoft Project 2007

Advantages	3

Closing	19

Interface Overview	9

New Features	3

Opening	7

What is	2

Milestones	72

Page Breaks	120, 125, 126, 148, 153

Page Setup	137, 148, 153, 154

Footers tab	141

Header tab	139

Legend tab	142

Margins tab	138

Opening from File menu	137

Opening from Print Preview	147

Opening from Project Guide	150

Page tab	137

View tab	143

PivotTables	3

Planning a Project	47

Popular Shortcut Keys	14

Print Preview

Navigating	147

Opening from File menu	145

Opening from Page Setup	138, 144

Opening from Project Guide	152

Overview	146

Printing

Commands	147

From Page Setup	147

From Print Preview	147

Print current view as a report	149

Print dialogue	148

Project Equation	72

Project Window	10

Revised Custom Field Structure	5

Scroll Bars	10

Status Bar	10

Task Drivers	5

Task Panes

About	10

Components of	17

Critical Path	112

New Project	49

Project guide	1, 17, 18, 20, 24, 25, 26, 57, 59, 62, 64, 77, 84, 91, 99, 112, 149, 153

Tasks

And deadlines	82, 83, 84, 86

And milestones	72

Changing duration via Gantt chart	66

Changing duration via Task Entry view	65

Creating via Project Guide	64

Creating via Task Entry view	64

Critical	111

Deleting	67

Duration abbreviations	65

Indenting	77, 78

Inserting	66

Moving	66

Out-denting	76, 77

Recurring	73

Subtasks	75

Summary	76

Task Information	46, 68, 72, 74, 80

Task types	69

Timescale

Changing via zoom	127

Formatting	95

Samples	96

Title Bar	9

Toolbars

Components of	10

Formatting	23

Missing buttons	24

Show Buttons on Two Rows command	24

Showing and Hiding	13

Standard	21

What are?	10

Top Down Budgeting	5

View Commands

Calendar view	93

Minimize, maximize, and restore	10

More Tables	102, 103

More Views	132

Using View menu	132

View Bar	130

Window menu	32

Zoom via dialogue	128

Zoom via toolbar	127

Visual Reports	3, 4